# THE B2M LEVERAGE PLAN

## How Boys 2 Men Powers Lamplighters Year Two

Rochester Omega Lamplighters × Boys 2 Men × UPrep Golf · 2026–27

Prepared by Coach G

## THE STRATEGIC READ

Most people look at the B2M partnership and see community service. That's the small version.

B2M solves three of the chapter's four Year Two problems at once.

| Chapter Problem | How B2M Solves It |
| --- | --- |
| Not enough committed adult volunteers | B2M families are already bought in, already know Coach G, and already have sons in the pipeline. They are the highest-probability volunteer pool in Rochester — and nobody has formally asked them. |
| Tier 2 Lamplighters need real leadership reps, not worksheets | Planning and running a monthly event for 9-to-13-year-olds is the single best leadership laboratory available, and it costs the chapter almost nothing. |
| Recruitment pipeline for the next class | 39 boys ages 9–13 are already in the program. The oldest are 13 — they age into Lamplighters eligibility next year. |
| (Not solved by B2M: meeting space and budget — those need separate work.) |  |

Coach G directs both programs. That is not a scheduling coincidence — it is the leverage.

## THE PIPELINE, MADE VISIBLE

Boys 2 Men (9–13) → Rochester Omega Lamplighters (14–18) → Omega Psi Phi (adult)

A 10-year-old at 585 Dream Camp who watches a 16-year-old Lamplighter run the room doesn't have to imagine the pipeline. He is looking at it. And when UPrep Golf student-athletes are in that room too, he sees it from two directions instead of one.

This is a three-way mentoring structure, not a hand-off.

## HOW IT WORKS

### THE CADENCE

| Window | Cadence | Location |
| --- | --- | --- |
| School year (Sept–June) | One signature 18 Opportunities event per month, mirroring that month's Lamplighters 18-O theme | 585 Dream Camp, 321 Post Ave |
| Summer (July–August) | Biweekly, layered into B2M's existing M–F day-camp block | 585 Dream Camp |

Start monthly. Treat biweekly as the target once the facilitator bench is built and the first few events run clean. A cadence that actually happens every time beats a more frequent one that starts slipping.

### THE CONTENT RULE

Content adapts the 18-O monthly theme — belonging, excellence, relationships, purpose, leadership, legacy — into age-appropriate B2M activities. Most events run through B2M's existing 9-section Program Framework with an opportunity theme layered on top. Golf is one occasional activity lane, not the spine.

This adds to what B2M already runs. It does not replace it.

### THE EVENT SHAPE (90 minutes, matching B2M's block structure)

| Time | Segment | Who Runs It |
| --- | --- | --- |
| 0:00–0:10 | Circle Up — welcome, standard, theme of the month | Tier 2 Lamplighter |
| 0:10–0:30 | Teach — the scaled-down 18-O concept | Tier 2 Lamplighter + UPrep Golf athlete |
| 0:30–1:00 | Stations — 2–3 rotations (skill, money trail, build/pitch) | Tier 1 Lamplighters + golf athletes |
| 1:00–1:20 | Build / Do — B2M boys produce something | Facilitator bench |
| 1:20–1:30 | Money Trail Debrief + Close | Tier 2 Lamplighter |

Every event ends with the same four questions: What did you see? Who gets paid? What skills did those people need? Where could you enter?

## THE MONTHLY EVENT MAP

Each B2M event mirrors that month's Lamplighters theme, scaled for ages 9–13.

| Month | Lamplighters Theme | B2M Event | B2M Takeaway |
| --- | --- | --- | --- |
| SEP | I Belong Here | Kickoff: I Belong Here | Introductions, the standard, first putting/build station |
| OCT | Mother–Son: Value | I Present With Excellence | Handshakes, presentation, how to walk into a room |
| NOV | Show Me the Money | I Follow the Money | Who gets paid inside one business they already know |
| DEC | Brotherhood + Network | I Build Relationships | The check-in call, the follow-up, being a brother on purpose |
| JAN | Father/Mentor–Son: Provision | I Understand My Numbers | Grades, money, effort — tracked out loud |
| FEB | STEM + The Game | I Understand Technology | Hands-on build or simulator station |
| MAR | Youth + Power | I Lead | Every B2M boy leads one piece under a Lamplighter's coaching |
| APR | Entrepreneurship | I Create Opportunity | Scaled pitch session — direct runway to B2M's summer Expo |
| MAY | College + Career Capital | I Understand Careers | Career exploration ahead of summer camp |
| JUN | Ownership | Summer Handoff | Transition to biweekly summer cadence |

Note the April alignment: B2M's own summer program culminates in an Entrepreneurship Expo where every boy pitches a real business. The April Lamplighters event is deliberate preparation for it — and Lamplighters who coach that pitch session in April are the natural judges and coaches at the Expo in August.

## ROLES & OWNERSHIP

| Who | Role |
| --- | --- |
| Coach G | Bridges all three programs; sets the shared monthly theme; owns Lamplighters-side content |
| Khadija Yawn / Roc Royal Inc. | B2M operator — approves B2M-side commitments, facility use at 585 Dream Camp, B2M-side logistics and parent communication |
| Damian Brown, B2M Assistant Director | B2M-side logistics, safety, scheduling. His rotation and times are inviolable — never invent or adjust them. |
| Tier 2 Lamplighters (Light Leaders) | Plan and deliver the monthly events; lead the circle, the teach, and the debrief |
| Tier 1 Lamplighters | Run stations, support logistics, media, and guest care |
| UPrep Golf student-athletes | Lead golf-specific activity lanes; co-run general 18-O sessions |
| Lamplighters Advisory Board / Committee | Oversight and outcomes review |

## THE VOLUNTEER PLAY (THE PART EVERYONE SKIPS)

Every B2M event is a volunteer recruitment event. Run it deliberately:

- Invite B2M parents to attend the monthly event, not just drop off.

- Give them something to watch — their son being led by a young man who was in his seat four years ago.

- Make one clear ask at the close. Not "we need help." Specifically: "We need two adults who can give us four hours a month. Here's exactly what that looks like. Who's in?"

- Capture the commitment in writing that day — name, role, hours, months.

- Follow up within 48 hours with the onboarding packet.

Target: 4–6 new committed adult volunteers from the B2M family pool by December 2026. That is what unlocks the class size the chapter actually wants.

## WHAT EACH SIDE GAINS

B2M gains structured, opportunity-framed programming delivered by near-peer role models just a few years older — the pipeline becomes something a 10-year-old can see, and he sees it from two directions instead of one.

Lamplighters gains real leadership and facilitation reps for its own members, documented service hours with substance, a pre-qualified recruitment pool, and access to the most likely source of new adult volunteers in the city.

UPrep Golf gains a direct mentoring role for its student-athletes and proof the 18-O framework works as a youth-development model beyond one sport.

## SUCCESS MEASURES

| Measure | Target |
| --- | --- |
| Monthly events actually run against the plan | 10 of 10 |
| B2M participation rate per event | 70%+ of enrolled |
| Lamplighters serving as facilitators | 100% of Tier 2; 50%+ of Tier 1 |
| Facilitation reps per Tier 2 Lamplighter | 4+ |
| New adult volunteers recruited from B2M families | 4–6 by December |
| Long game: B2M members who apply to Lamplighters at 14 | Tracked from the first cohort forward |

## NEXT STEPS TO ACTIVATE

- Confirm with Khadija Yawn / Roc Royal Inc. as the B2M operator — she approves B2M-side commitments and facility use. Make one clear ask: monthly 18-O event, 90 minutes, Lamplighter-facilitated, at 585 Dream Camp.

- Confirm logistics directly with Damian Brown — day, time, and how the event fits his rotation. His schedule governs.

- Recruit the first joint facilitator bench — Tier 2 Lamplighters plus UPrep Golf student-athletes willing to plan and run events.

- Run a facilitator training before the September event: the event shape, the teach, the stations, the debrief, and how to hold a room of 9-to-13-year-olds.

- Set the September date and lock the monthly cadence.

- Build the volunteer ask script and use it at every single event from September forward.

## OPEN ITEMS

- [CONFIRM] Khadija's approval for the school-year monthly cadence

- [CONFIRM] Damian Brown's day/time slot within the school-year schedule

- [CONFIRM] Whether B2M continues at the same scale during the school year, or whether the school-year version is a smaller cohort

- [CONFIRM] Transportation for Lamplighters to 585 Dream Camp (321 Post Ave)

- [CONFIRM] Any background-check or clearance requirement for youth-serving-youth facilitation under Roc Royal's policies

- [CONFIRM] UPrep Golf student-athlete availability and school approval for off-site mentoring

Rochester Omega Lamplighters × Boys 2 Men × UPrep Golf • The pipeline is the product.